## Sprint 3 Requirements
GoPhishFree – Sprint 3 Requirements
Sprint Period: February 23 – March 8, 2026 ¦ Team: Ty Farrington, Andrew Reyes, Brett Suhr, Nicholas Holmes, Kaleb Howard
Req ID | Requirement | Story Pts | Priority | Sprint | Status
1 | Baseline extension UI | 5 | High | 1 | Done
2 | Email content extraction | 5 | High | 1 | Done
3 | Risk indicator button | 3 | High | 1 | Done
4 | Report dashboard | 5 | High | 1 | Done
5 | Architecture definition | 3 | High | 1 | Done
6 | Develop an initial phishing detection model design | 5 | High | 2 | Done
7 | Train the phishing detection model using labeled phishing email datasets | 8 | High | 2 | Done
8 | Validate the trained phishing detection model for classification accuracy | 5 | High | 2 | Done
9 | Integrate the trained phishing detection model into the extension's analysis pipeline | 8 | High | 2 | Done
10 | Generate a phishing risk score for the selected email using the integrated model | 5 | High | 2 | Done
11 | Display the phishing risk score within the report dashboard | 3 | Medium | 2 | Done
12 | Display the primary reasons contributing to the phishing risk score | 5 | Medium | 2 | Done
13 | Identify and display suspicious links found in the email | 5 | Medium | 2 | Done
14 | Local analysis requirement | 3 | High | 1 | Done
15 | Unified calibrated model refinement | 8 | High | 3 | In Progress
16 | Post-model intelligence layer | 5 | High | 3 | In Progress
17 | Fish award system and collection panel | 5 | Medium | 3 | Done
18 | Fish tank persistence | 5 | Medium | 3 | Done
19 | Analysis history | 3 | Medium | 3 | Planned
20 | Visual and UI polish | 3 | Medium | 3 | Planned
21 | Display loading indicators while email analysis is in progress | 2 | Medium | 2 | Done
22 | Display clear error messages when analysis cannot be completed | 3 | Medium | 2 | Done
23 | Sensitivity controls | 3 | Medium | 3 | Planned
24 | User feedback mechanism | 5 | Medium | 3 | Planned
25 | Performance optimization | 5 | Medium | 3 | Planned
26 | Iterative model improvement loop | 8 | Medium | 3 | In Progress
27 | AI enhancement (Cloud BYOK) | 8 | Low | 4 | Backlog
28 | DNS-over-HTTPS validation | 5 | Low | 4 | Backlog
29 | Chrome Web Store packaging | 3 | High | 1 | Planned
30 | Deployment documentation | 3 | High | 1 | Done

## Stretch Goals
Sprint 3 – Stretch Goals (Ahead-of-Schedule Items)
Sprint Period: February 23 – March 8, 2026 ¦ Team: Ty Farrington, Andrew Reyes, Brett Suhr, Nicholas Holmes, Kaleb Howard
Item | Related Req | Description | Status
Unified 64-feature calibrated model | Req 15 (Sprint 3) | Replace the two-model pipeline with a single unified Random Forest using isotonic calibration. | In Progress
BEC/Linkless detection features | Req 15 (Sprint 3) | Add FinancialRequestScore, AuthorityImpersonationScore, PhoneCallbackPattern, ReplyToMismatch, and IsLinkless. | In Progress
Attachment analysis features | Req 15 (Sprint 3) | Add HasAttachment, AttachmentCount, RiskyAttachmentExtension, DoubleExtensionFlag, and AttachmentNameEntropy. | In Progress
Trusted domain whitelist (500+ domains) | Req 16 (Sprint 3) | Implement comprehensive whitelist and separate free email providers. | In Progress
Post-model intelligence layer | Req 16 (Sprint 3) | Add BEC boosts, trusted domain dampening, and newsletter detection logic. | In Progress
User-managed custom trusted domains | Req 16 (Sprint 3) | Allow users to add/remove trusted domains via popup UI. | Planned
Synthetic training data augmentation | Req 15 (Sprint 3) | Generate additional synthetic phishing and legitimate samples. | In Progress
Fish award system and collection panel | Req 17 (Sprint 3) | Award themed fish and render animated fish tank dashboard. | Done

## Source Files
Sprint 3 – Source Files to Create/Modify
Sprint Period: February 23 – March 8, 2026 ¦ Team: Ty Farrington, Andrew Reyes, Brett Suhr, Nicholas Holmes, Kaleb Howard
File | Planned Changes | Status
content.js | Enhance unified inference pipeline and post-model intelligence integration. | In Progress
featureExtractor.js | Add BEC/linkless and attachment feature expansion. | In Progress
background.js | Refine AI gating logic and provider handling. | Planned
popup.html | Add fish tank UI polish and sensitivity controls interface. | Planned
popup.js | Add fish persistence wiring, history view, and feedback hooks. | In Progress
train_model.py | Retrain unified calibrated model with expanded synthetic dataset. | In Progress
manifest.json | Update permissions if required for new features. | Planned

## Deliverables Summary
Sprint 3 – Deliverables Summary
Sprint Period: February 23 – March 8, 2026 ¦ Team: Ty Farrington, Andrew Reyes, Brett Suhr, Nicholas Holmes, Kaleb Howard
Metric | Target
Requirements to Complete | 10 (+ stretch goals)
Story Points | 50
Source Files to Create/Modify | 7 (train_model.py, content.js, featureExtractor.js, background.js, popup.html, popup.js, manifest.json)
ML Features | 64 (unified schema, refined)
Feature Groups | URL/Email, Custom Rules, DNS, Deep Scan, BEC/Linkless, Attachment, Context Flags
Decision Trees | 200 (isotonic calibrated)
Target Model Accuracy | >96% overall target after refinement
Model Type | Random Forest + CalibratedClassifierCV (isotonic)
Dataset Size | ~40,000 samples after augmentation
Training/Test Split | 80/20 stratified
Score Formula | riskScore = round(100 x calibrated_probability)
Trusted Domains | 500+ built-in + user custom
Risk Score Range | 0 - 100 (4 risk levels)
Risk Levels | Friendly Fish (0-49), Suspicious Fish (50-75), Phishy Puffer (76-89), Mega Phish Shark (90-100)
Documentation Updates | README, MODEL_NOTES, EVALUATION_RESULTS, Sprint 3 docs
Sprint Duration | 14 days
Team Members | 5

## ML Model Artifacts
Sprint 3 – Machine Learning Model Artifacts
Sprint Period: February 23 – March 8, 2026 ¦ Team: Ty Farrington, Andrew Reyes, Brett Suhr, Nicholas Holmes, Kaleb Howard
Artifact | Description
Training Script (train_model.py) | Retrains unified calibrated Random Forest with expanded synthetic phishing coverage and improved feature engineering.
Training Dataset | Augmented phishing_legitimate dataset expanded beyond ~36k samples with BEC and attachment scenarios.
Unified Model (model_unified.json) | Updated Random Forest with refined calibration and feature weights for in-browser inference.
Feature Name File (feature_names_unified.json) | Ordered list of unified features aligned with FeatureExtractor updates.
Calibrated Model (model_unified_calibrated.pkl) | Offline evaluation model used for validation and iterative improvement.