## Sheet1
GoPhishFree – Sprint 4 Requirements
Sprint Period: February 23 – March 8, 2026 ¦ Team: Ty Farrington, Andrew Reyes, Brett Suhr, Nicholas Holmes, Kaleb Howard
Req ID | Requirement | Story Pts | Priority | Sprint | Status
1 | Baseline extension UI | 5 | High | 1 | Done
2 | Email content extraction | 5 | High | 1 | Done
3 | Risk indicator button | 3 | High | 1 | Done
4 | Report dashboard | 5 | High | 1 | Done
5 | Architecture definition | 3 | High | 1 | Done
6 | Develop an initial phishing detection model design | 5 | High | 2 | Done
7 | Train the phishing detection model using labeled phishing email datasets | 8 | High | 2 | Done
8 | Validate the trained phishing detection model for classification accuracy | 5 | High | 2 | Done
9 | Integrate the trained phishing detection model into the extension's analysis pipeline | 8 | High | 2 | Done
10 | Generate a phishing risk score for the selected email using the integrated model | 5 | High | 2 | Done
11 | Display the phishing risk score within the report dashboard | 3 | Medium | 2 | Done
12 | Display the primary reasons contributing to the phishing risk score | 5 | Medium | 2 | Done
13 | Identify and display suspicious links found in the email | 5 | Medium | 2 | Done
14 | Local analysis requirement | 3 | High | 1 | Done
15 | Unified calibrated model refinement | 8 | High | 3 | Done
16 | Post-model intelligence layer | 5 | High | 3 | Done
17 | Fish award system and collection panel | 5 | Medium | 3 | Done
18 | Fish tank persistence | 5 | Medium | 3 | Done
19 | Analysis history | 3 | Medium | 3 | Done
20 | Visual and UI polish | 3 | Medium | 3 | Done
21 | Display loading indicators while email analysis is in progress | 2 | Medium | 2 | Done
22 | Display clear error messages when analysis cannot be completed | 3 | Medium | 2 | Done
23 | Sensitivity controls | 3 | Medium | 4 | Planned
24 | User feedback mechanism | 5 | Medium | 3 | In Progress
25 | Performance optimization | 5 | Medium | 3 | Done
26 | Iterative model improvement loop | 8 | Medium | 3 | Done
27 | AI enhancement (Cloud BYOK) | 8 | Low | 4 | Planned
28 | DNS-over-HTTPS validation | 5 | Low | 4 | Planned
29 | Chrome Web Store packaging | 3 | High | 4 | Planned
30 | Deployment documentation | 3 | High | 1 | Done
31 | Website navigation and functionality | 8 | High | 4 | In Progress
31 | Deep scan visual / virtual environment | 5 | Medium | 4 | In Progress