# GoPhishFree — Sprint 1 Requirements

Project: GoPhishFree – AI-Powered Phishing Detection Chrome Extension

Team: Ty Farrington, Andrew Reyes, Brett Suhr, Nicholas Holmes, Kaleb Howard

Sprint Period: January 26 – February 8, 2026

## Overview

Sprint 1 will focus on building the foundation of GoPhishFree, a Chrome extension that helps users identify phishing emails in Gmail. The goal is to set up the project, create the basic extension interface, build out the core email scanning functionality, and begin developing the phishing detection model. We also plan to get a head start on some features planned for later sprints, including the fish tank popup and model training.

## Sprint 1 Requirements (From Requirements Stack)

The following requirements are assigned to Sprint 1 in the project requirements stack. These are the primary goals the team will work toward completing this sprint.

| Req ID | Requirement | Story Pts | Priority |
| --- | --- | --- | --- |
| 1 | Define and display a baseline extension interface framework | 5 | High |
| 2 | Extract relevant content and metadata from a user-selected email | 5 | High |
| 3 | Display a phishing risk indicator button for the selected email | 3 | High |
| 4 | Open a basic report dashboard when the user clicks the risk indicator button | 5 | High |
| 5 | Define the feature set and architecture for the phishing detection model | 3 | High |
| 14 | Perform all phishing analysis locally without transmitting email data externally | 3 | High |
| 29 | Package the extension for public distribution | 3 | High |
| 30 | Publish the extension to the Chrome Web Store | 5 | High |

## Stretch Goals (Ahead-of-Schedule Items)

If time permits, the team will also begin work on the following items from later sprints to get ahead of the project timeline.

| Item | Related Req | Description |
| --- | --- | --- |
| Set up the GitHub repository | – | Create the shared GitHub repo, set up branching, and establish the team workflow. |
| Create project README and documentation | – | Write a README with project overview and quick start instructions. Create a setup guide, project summary, and feature documentation. |
| Train an initial phishing detection model | Req 6–8 (Sprint 2) | Train a machine learning model on a dataset of phishing and legitimate emails. The model will be trained on 20 features and we are aiming for at least 90% accuracy. |
| Export model data for use in the extension | Req 9 (Sprint 2) | Export the trained model’s feature weights and settings to files the extension can use. |
| Build the fish tank popup display | Req 18 (Sprint 3) | Create an animated fish tank aquarium in the extension popup with swimming fish, bubbles, seaweed, and other decorations. |
| Track and store fish collection across sessions | Req 19 (Sprint 3) | Save fish collection data so it persists when the browser is closed and reopened. |
| Show a visual animation when a new fish is caught | Req 20 (Sprint 3) | Display a “Fish Caught!” animation when an email is scanned, showing the fish type earned. |
| Maintain a history of analyzed emails | Req 23 (Sprint 3) | Keep a list of recently scanned emails with their risk scores, viewable in the popup dashboard. |
| Add comprehensive code comments | – | Document all source code files with header comments (authors, dates, descriptions) and line-by-line comments for maintainability. |

## Sprint 1 Planning Summary

| Metric | Value |
| --- | --- |
| Sprint 1 Requirements | 8 |
| Sprint 1 Story Points | 32 |
| Stretch Goal Items | 9 |
| Sprint Duration | 14 days |
| Team Members | 5 |