## Sprint 6 Requirements
GoPhishFree – Sprint 6 (Final Sprint) Requirements
Sprint Period: April 12 – April 26, 2026 ¦ Team: Ty Farrington, Andrew Reyes, Brett Suhr, Nicholas Holmes, Kaleb Howard
Req ID | Requirement | Story Pts | Priority | Sprint | Status
1 | Baseline extension UI | 5 | High | 1 | Done
2 | Email content extraction | 5 | High | 1 | Done
3 | Risk indicator button | 3 | High | 1 | Done
4 | Report dashboard | 5 | High | 1 | Done
5 | Architecture definition | 3 | High | 1 | Done
6 | Develop an initial phishing detection model design | 5 | High | 2 | Done
7 | Train the phishing detection model using labeled phishing email datasets | 8 | High | 2 | Done
8 | Validate the trained phishing detection model for classification accuracy | 5 | High | 2 | Done
9 | Integrate the trained phishing detection model into the extension analysis pipeline | 8 | High | 2 | Done
10 | Generate a phishing risk score for the selected email using the integrated model | 5 | High | 2 | Done
11 | Display the phishing risk score within the report dashboard | 3 | Medium | 2 | Done
12 | Display the primary reasons contributing to the phishing risk score | 5 | Medium | 2 | Done
13 | Identify and display suspicious links found in the email | 5 | Medium | 2 | Done
14 | Local analysis requirement | 3 | High | 1 | Done
15 | Unified calibrated model refinement | 8 | High | 3 | Done
16 | Post-model intelligence layer | 5 | High | 3 | Done
17 | Fish award system and collection panel | 5 | Medium | 3 | Done
18 | Fish tank persistence | 5 | Medium | 3 | Done
19 | Analysis history | 3 | Medium | 3 | Done
20 | Visual and UI polish | 3 | Medium | 3 | Done
21 | Display loading indicators while email analysis is in progress | 2 | Medium | 2 | Done
22 | Display clear error messages when analysis cannot be completed | 3 | Medium | 2 | Done
23 | Sensitivity controls | 3 | Medium | 4 | Done
24 | User feedback mechanism | 5 | Medium | 4 | Done
25 | Performance optimization | 5 | Medium | 3 | Done
26 | Iterative model improvement loop | 8 | Medium | 3 | Done
27 | AI enhancement (Cloud BYOK) | 8 | Low | 4 | Done
28 | DNS-over-HTTPS validation | 5 | Low | 4 | Done
29 | Chrome Web Store packaging | 3 | High | 4 | Done
30 | Deployment documentation | 3 | High | 1 | Done
31 | Website navigation and functionality | 8 | High | 4 | Done
32 | Deep scan visual / virtual environment | 5 | Medium | 4 | Done
33 | Submit extension to Chrome Web Store for review and address approval feedback | 8 | High | 5 | Done
34 | Add Terms of Service & Privacy Policy agreement for Chrome Web Store listing | 5 | High | 5 | Done
35 | Add developer creditation with linked website attribution for all team members | 5 | Medium | 5 | Done
36 | Address Chrome Web Store reviewer feedback and required policy changes | 8 | High | 5 | Done
37 | Final extension polish and production hardening for store approval | 5 | High | 5 | Done
38 | Website update with team member profiles and project creditation links | 5 | Medium | 5 | Done
39 | Final regression testing across Gmail UI variants | 3 | Medium | 5 | Done
40 | Sprint 5 documentation and final project deliverables | 3 | High | 5 | Done
41 | Monitor Chrome Web Store review status and respond to reviewer feedback within 48 hours | 8 | High | 6 | In Progress
42 | Address any Chrome Web Store policy violations or required changes upon denial | 8 | High | 6 | Planned
43 | Publish extension to Chrome Web Store upon approval and verify live listing | 5 | High | 6 | Planned
44 | Update GoPhishFree website homepage with Chrome Web Store install link upon publication | 3 | High | 6 | Planned
45 | Verify Google Search Console site verification and sitemap indexing are active | 3 | Medium | 6 | Planned
46 | Verify all Google accreditation and attribution links on website are approved and indexed | 5 | Medium | 6 | Planned
47 | Final end-to-end regression testing on the published extension from Chrome Web Store | 5 | High | 6 | Planned
48 | Final project documentation, sprint retrospective, and capstone deliverables | 3 | High | 6 | Planned
Sprint 6 Summary
Total Requirements (Cumulative) |  | 48
Sprint 6 New Requirements |  | 8
Sprint 6 Story Points |  | 40
Sprint Duration |  | 14 days (Apr 12 – Apr 26, 2026)
Team Members |  | 5
Sprint 6 Focus Areas |  | CWS approval/denial response, publication, website CWS link, Google accreditation verification